## Sheet1
Committee | When | Task | Done | Comments
Concert Chair | November | Ask Steve Ramsey and Orchestra to perform at next year's concert
Concert Chair | November | Ask cathedral for rehearsal and concert space
Concert Chair | May | Ask grantee to speak at concert
Concert Chair | May | Ask clergy to offer prayers
Concert Chair | May | Ask ushers to participate
Concert Chair | May | Ask board members to help with reception
Concert Chair | May | Ask cathedral for fundraising clearance
Concert Chair | May | Outline cathedral order of program for concert
Concert Chair/Donor manager | July | Send solicitation letter to past donors and VFWs
Communications | July | Ask Cathedral to post information about concert in bulletin
Communications | July | Ask webmaster to post concert info on website and Facebook-Fundraising page
Communications | July | Distribute flyer and send press release via email to newspapers and other p.r. sources
Communications | July | Arrange on-air advertising if pertinent to MPR or other radio
Communications | July | Develop updated concert trifold brochure
Concert Chair/Donor Manager | July | Send trifold to donors and VFWs
Communications | July | Develop updated concert flyer
Communications | July | Send flyer to cathedral, local coffee houses, orchestra members
Communications | September | Develop Printed program with info from Steve Ramsey
Communications | September | Send email to grantees with concert flyer
Concert Chair | September | Order poppies if needed
Communications | October, second week | Finalize print program with known donors and orchestra personnel with Steve Ramsey and print, about 200
Concert Chair | October, last week | Finalize rehearsal details with cathedral and orchestra and attend rehearsal
Concert Chair | October, last week | Check that food has been ordered by reception committee with appropriate tables, etc.
Concert Chair | October, last week | Double check logistics with speakers
Concert Chair | October, last week | Make sure emcee/Wells president has order of program and can introduce speakers
Concert Chair | October, last week | Make sure ushers are on deck for concert
Concert Chair | November day of concert | Greet orchestra and board help with set up
Chair | November day of concert | Place US flags on stage
Ushers | November day of concert | Locate programs, poppies
Ushers | November day of concert | Collect offering and count in bags, usually stashing in safe for later deposit
Ushers/Chair | November day of concert | Make sure all checks made out to Wells, not St. Mark's-if so, ask St. Mark's for reimbursement
Chair | November, second week | Announce total of donations for concert
Chair/Lin Shurtleff, acct. | Ongoing | Send thank yous to donors-ongoing
Chair | November, second week | Thank yous to speakers and clergy
All Committees | late November | Review concert for what went well and what did not
Communications | late November | Update web page and Facebook with concert pics